## general_report
Key | Summary | Issue Type | Status | Priority | Assignee | Reporter | Creator | Images | Description | Epic Link | Rank | Story Points
CH-117 | Mobile Optimization: Raise landing screen buttons on mobile | Bug | To Do | Critical | Unassigned | bblankenship | bblankenship |  |  | Navigation | 0¦hzzykp: | 8
CH-114 | Inbox - Reply to message replaces recipients name with sender name | Bug | To Do | Critical | Unassigned | nabdesai | nabdesai | _thumb_17949.png | When replying to an existing message and clicking Send, the system replaces the To field with the sender's name | Messaging | 0¦hzzykx: | 3
CH-72 | Edit Profile - Selecting Cancel displays edits | Bug | To Do | Critical | Unassigned | nabdesai | nabdesai |  | If a user makes edits to their profile (General or Household Members) and clicks [Cancel], the system still displays the edits as if they were saved. If the user navigates away and returns to the page the correct information is displayed | Manage my profile | 0¦hzzyl1: | 5
CH-80 | Edit Profile - Form Restrictions | Bug | To Do | Critical | Unassigned | nabdesai | nabdesai |  | Currently we do not have any form restrictions when the user and household profile editing pages. This opens us up to some security risks. For future versions we should implement a backend and front end form validation and controls (calendar, lists, alphanumeric, etc) | Manage my profile | 0¦hzzyl3: | 5
CH-86 | Inbox - Message removed from conversation history if a second message is sent | Bug | To Do | Critical | Unassigned | nabdesai | nabdesai |  | If a user replies with a message and then sends a second message, the first message is overwritten/removed | Messaging | 0¦hzzyl4: | 3
CH-100 | Icon disappears in Edge browser | Bug | To Do | Critical | Unassigned | nabdesai | nabdesai | _thumb_17891.png | Profile Icon disappears when not active in Edge | Navigation | 0¦hzzyl4:i | 2
CH-115 | Mobile - Navigation page does not extend to the full screen | Bug | To Do | Critical | Unassigned | nabdesai | nabdesai | _thumb_17951.png | On mobile devices, if the user selects the menu and scrolls down, they will see the overlay does not extend throughout the page | Navigation | 0¦hzzyl4:r | 5
CH-65 | Account Creation - Special Characters in email address remove homescreen icons | Bug | To Do | Critical | Unassigned | nabdesai | nabdesai | _thumb_17814.png | Users are able to insert special characters as part of their email address. After creating the account, the user is placed on the dashboard without navigation Icons. The following special characters trigger the issue ! # $ % ^ & * { } ' + | Establish a new account | 0¦hzzyl4:v | 2
CH-46 | Mobile Optimization: Optimize/compress images | Task | To Do | Major | Unassigned | lomelchenko | lomelchenko |  |  | Landing Page | 0¦hzzyl4:x | 2
CH-104 | Add Title to 'Inbox' to Inbox page | Bug | To Do | Major | Unassigned | nabdesai | nabdesai |  | For consistency add Inbox header to the Inbox page | Messaging | 0¦i03dxf:i | 5
CH-106 | As a user I want to be able to actively receive responses from the messaging system | User Story | To Do | Major | Unassigned | jklockenbrink | jklockenbrink |  |  | Messaging | 0¦i03dxg: | 21
CH-74 | Hook up message persistence to the front-end | Task | To Do | Major | Unassigned | lomelchenko | lomelchenko |  |  | Messaging | 0¦i03dxi: | 13
CH-71 | Update Favicon | Task | Done | Major | Unassigned | lomelchenko | lomelchenko |  |  |  | 0¦i03dyf:1 | 2
CH-52 | As a user I want to be able to access a detailed page on a facility that I select | User Story | To Do | Major | Unassigned | jklockenbrink | jklockenbrink |  |  | Search Facilities | 0¦i03dyg: | 3
CH-35 | As a user I would like to apply to be a foster parent | User Story | To Do | Major | Unassigned | jklockenbrink | jklockenbrink |  |  | Establish a new account | 0¦i03dyi: | 34
CH-23 | As a user I want to be able to delete a message | User Story | To Do | Major | Unassigned | jklockenbrink | jklockenbrink |  |  | Messaging | 0¦i03dyj: | 5
CH-38 | As a user I would like to see FAQs | User Story | To Do | Major | Unassigned | jklockenbrink | jklockenbrink |  |  | Landing Page | 0¦i03dyp: | 5
CH-39 | As a user I would like to see an about us | User Story | To Do | Major | Unassigned | jklockenbrink | jklockenbrink |  |  | Landing Page | 0¦i03dyr: | 3
CH-45 | As a user, I want to view the map on my mobile device | User Story | To Do | Major | Unassigned | lomelchenko | lomelchenko |  |  | Search Facilities | 0¦i03e2h: | 5
CH-47 | Refactor code - remove remaining references to REX | Task | To Do | Major | Unassigned | lomelchenko | lomelchenko |  |  |  | 0¦i03e2k: | 13
CH-62 | Facility Search - Show warning message when you search zip code outside of CA | Story | To Do | Major | Unassigned | lomelchenko | lomelchenko |  |  | Search Facilities | 0¦i03ekl: | 5
CH-63 | Toolbar Label Alignment | Bug | To Do | Major | Unassigned | nabdesai | nabdesai | _thumb_17810.png | The toolbar icon labels are rendering are left-justified rather than centered with respect to the icon | Navigation | 0¦i03elp: | 3
CH-64 | Toolbar Icon not level in Firefox | Bug | To Do | Major | Unassigned | nabdesai | nabdesai | _thumb_17811.png | The Inbox and Help icons are not rendering on the same plane as the Profile and Facilities icons in Firefox only. | Navigation | 0¦i03elx: | 3
CH-67 | Mobile - iOS My Profile Controls Aesthetics | Bug | To Do | Major | Unassigned | nabdesai | nabdesai | _thumb_17823.png _thumb_17824.png | The display page on the iPhone 6 plus needs aesthetics improvement | Manage my profile | 0¦i03enx: | 3
CH-78 | Edit Profile - Services and Certification additions not bulleted | Bug | To Do | Major | Unassigned | nabdesai | nabdesai | _thumb_17863.png _thumb_17862.png | Currently there isn't any functionality for adding new services or certifications and have the system bullet list the results. | Manage my profile | 0¦i03ezp: | 3
CH-79 | As a user, I would like to be able to search for facilities without logging in /creating account | User Story | To Do | Major | Unassigned | bblankenship | bblankenship |  |  | Search Facilities | 0¦i03f0d: | 3
CH-81 | Mobile - Menu displayed on Landing Page | Bug | To Do | Major | Unassigned | nabdesai | nabdesai | _thumb_17866.png | On mobile/condensed browsers, the Menu (Profile, Inbox, Facilities) is displayed even though a user is not logged in. This should be removed to avoid confusion. | Navigation | 0¦i03f1p: | 2
CH-82 | Mobile - Navigation Menu does not collapse after to selection | Bug | To Do | Major | Unassigned | nabdesai | nabdesai |  | For mobile, after a user makes a selection on the navigation menu, the pane does not retract | Navigation | 0¦i03f25: | 3
CH-84 | Inbox - Notifications reappear after viewing messages | Bug | To Do | Major | Unassigned | nabdesai | nabdesai |  | The system restores messages as unread after navigating away and returning to the Inbox. Additionally, the icon always displays the notification | Messaging | 0¦i03f2t: | 8
CH-85 | Inbox - Date incorrect on Reply | Bug | To Do | Major | Unassigned | nabdesai | nabdesai | _thumb_17878.png | Reply message displays the incorrect Date | Messaging | 0¦i03f3h: | 5
CH-87 | Inbox - Toolbar alignment shifts on larger screens/windows | Bug | To Do | Major | Unassigned | nabdesai | nabdesai |  | The Inbox tool bar is slightly shift to the right when users navigate to the page. To reproduce; Enlarge browser to full screen Select 'My Profile' Select 'Facilities Near You' Select 'Inbox' -> shift occurs | Messaging | 0¦i03f45: | 3
CH-89 | Facilities - Cannot close info pop-up on map | Bug | Done | Minor | Unassigned | nabdesai | nabdesai |  | After selecting a facility on the map, users cannot close the subsequent information pop-up |  | 0¦i03f4l: | 3
CH-92 | Facilities - List Aesthetics on mobile | Bug | Done | Minor | Unassigned | nabdesai | nabdesai | _thumb_17882.png | The facility list pane flows into two sections of the page borders. This is more visual and may need a format change to the background color |  | 0¦i03f59: | 5
CH-93 | Facilities - Map does not reset on inital search zip code if map is moved | Bug | To Do | Major | Unassigned | nabdesai | nabdesai |  | If a user searches on a zip code, moves the map and then clicks search again, the map does not reset. | Search Facilities | 0¦i03f5h: | 3
CH-98 | Facilities - Pins removed when Search is double clicked | Bug | To Do | Major | Unassigned | nabdesai | nabdesai | _thumb_17890.png | If a user clicks [Search] twice against a zip code the pins are removed | Search Facilities | 0¦i03f7h: | 3
CH-9 | As a user I want to be able to contact my foster kids case worker from the kids layout | User Story | To Do | Minor | Unassigned | jklockenbrink | jklockenbrink |  |  | Manage my profile | 0¦i03f7n: | 3
CH-10 | As a user I want to be able to switch my email preferences in my profile information | User Story | To Do | Minor | Unassigned | jklockenbrink | jklockenbrink |  |  | Manage my profile | 0¦i03f7q: | 8
CH-14 | As a user I want to be able to refine my search results | User Story | To Do | Minor | Unassigned | jklockenbrink | jklockenbrink |  | By zip code, capacity | Search Facilities | 0¦i03f7r: | 8
CH-16 | As a user I want to be able to set up an appointment with a facility | User Story | To Do | Minor | Unassigned | jklockenbrink | jklockenbrink |  |  | Search Facilities | 0¦i03f7s: | 45
CH-19 | As a user I want to be able to tag messages for tracking purposes | User Story | To Do | Minor | Unassigned | jklockenbrink | jklockenbrink |  |  | Messaging | 0¦i03f7s:i | 8
CH-24 | As a user I want to be able to flag a message | User Story | To Do | Minor | Unassigned | jklockenbrink | jklockenbrink |  |  | Messaging | 0¦i03f7s:r | 5
CH-25 | As a user I want to be able to sort messages | User Story | To Do | Minor | Unassigned | jklockenbrink | jklockenbrink |  | By date / sender | Messaging | 0¦i03f7s:v | 5
CH-26 | As a user I want to be able to filer messages by content (search content) | User Story | To Do | Minor | Unassigned | jklockenbrink | jklockenbrink |  |  | Messaging | 0¦i03f7s:x | 20
CH-27 | As a user I want to be able to see messages in threaded format | User Story | To Do | Minor | Unassigned | jklockenbrink | jklockenbrink |  |  | Messaging | 0¦i03f7s:y | 20
CH-28 | As a ser I want to be able to archive messages | User Story | To Do | Minor | Unassigned | jklockenbrink | jklockenbrink |  |  | Messaging | 0¦i03f7s:z | 13
CH-29 | As a user I want to be able to mark messages as read/unread | User Story | To Do | Minor | Unassigned | jklockenbrink | jklockenbrink |  |  | Messaging | 0¦i03f7s:zi | 5
CH-90 | Facilities - map does not update facility list based when user moves map | Bug | To Do | Minor | Unassigned | nabdesai | nabdesai |  | If the user moves the map, the map does not update the facility list based upon the newly displayed region | Search Facilities | 0¦i03f7t: | 8
CH-91 | Facilities - Map does not zoom back into new zip code searches | Bug | To Do | Minor | Unassigned | nabdesai | nabdesai |  | If a user zooms out from a search and inputs a new zipcode to search, the map retains the current height/scale | Search Facilities | 0¦i03f7z: | 8
CH-95 | Inbox - Message Aesthetics | Bug | To Do | Minor | Unassigned | nabdesai | nabdesai | _thumb_17886.png | The conversation history is inconsistent with styling breaks. | Messaging | 0¦i03f82: | 5
CH-97 | Facilities - Zip code does not default to user set zip code | Bug | To Do | Minor | Unassigned | nabdesai | nabdesai |  | Zip code should prepopulate to the zipcode set by the user. | Search Facilities | 0¦i03f84: | 3
CH-59 | Account Creation - Email and Password not highlighted when incorrect | Bug | To Do | Minor | Unassigned | nabdesai | nabdesai | _thumb_17803.png | NOTE - this is only for consistency If a user inputs an invalid email or password, the system displays a message but does not highlight the field. If the user inputs an invalid First Name the system covers the text box | Establish a new account | 0¦i03fpv: | 5
CH-66 | Icons/links retaining focus border when selected | Bug | To Do | Minor | Unassigned | nabdesai | nabdesai | _thumb_17816.png | When selecting the toolbar icons or navigation links, the system continues to display the focus border until the user clicks away | Navigation | 0¦i03fpw: | 2
CH-83 | Inconsistent use of styling | Bug | To Do | Minor | Unassigned | nabdesai | nabdesai | _thumb_17875.png _thumb_17874.png _thumb_17873.png | Each page has a different style in terms of header and banner use. See attached screenshots for examples | Navigation | 0¦i03fpw:i | 8
CH-96 | Icon Spacing | Bug | To Do | Trivial | Unassigned | nabdesai | nabdesai | _thumb_17887.png | Icons are currently spaced by the text which results in a large gap between the Inbox and Facilities icons. **Suggestion, make Facility Near You two lines | Navigation | 0¦i03fpw:r | 2
CH-116 | Accommodate is lowercase | Bug | To Do | Trivial | Unassigned | nabdesai | nabdesai |  | On the manage profile page, "accommodate" is lowercase (inconsistant with the rest of the page) | Manage my profile | 0¦i03fpw:v | 1
CH-58 | Account Creation - invalid email format not displaying correct message | Bug | To Do | Trivial | Unassigned | nabdesai | nabdesai | _thumb_17802.png | System is displaying incorrect warning message when user inputs improper text in email field. | Establish a new account | 0¦i03fpw:x | 5